## Agile Backlog 1
Iteration 1 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 101. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority (light green)
Iteration 1
101 | User Authentication System | 5 | Backend Developer
102 | Core Database Schema Implementation | 7 | Full Stack Developer
103 | Volunteer Management Module | 4 | Full Stack Developer
104 | Basic Donation Processing | 3 | Backend Developer
105 | Initial Event Management Setup | 4 | UX/UI
…
Iteration 2
201 | Multi-Language Support | 3 | Frontend Developer
202 | Secure Authentication | 5 | Backend Developer
203 | Email Notifications and Update Alert for users | 4 | Backend Developer
Iteration 3
301 | Mobile App Version of NMS | 20 | Full Stack Developer
| Medium Priority (light blue) |  |  | Note: assigned medium and low tasks are prioritized but not yet assigned to iteration, nor estimated.
| Grant Tracking Framework |  | Backend Developer
| Impact Reporting Structure |  | Full Stack developer
Low Priority (pink)
| Dark Mode & UI Themes |  | Frontend Developer
| Advanced Analytics |  | Frontend Developer
| Badges for Completing Steps at UI |  | Ui Designer

## Iteration 1 Plan
Iteration Plan 1
Project | Designing a mobileApp for Nonprofit Management System
Team Names: | Global Scholars Team
Team Number: | G231
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
1 | UI/UX design task completed | KP | YES
2 | Setup backend | UM | YES
3 | Implement authentication | AP | YES
4 | Conduct usability testing | UM | YES
5 | Development environment setup | KP | YES
6 | Bug fixes from early testing | AP | YES
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Frontend (React.js) | Performance optimization, browser compatibility | KP
Backend (Node.js, Express.js) | API security, scalability issues | UM
Database (MongoDB on AWS) | Data integrity, backup strategy | AP
Hosting | Server downtime, cost management | KP
Authentication | Secure user login, session expiration | UM
DevOps | Deployment automation, rollback strategy | AP
3. Did your team visually track your progress by using tools such as Microsoft Project, SharePoint, Trello, etc.? Explain why you choose this tool.
Tracking Software Used | Why?
Trello | Easy-to-use Kanban board for tracking tasks, setting deadlines for the application.
Microsoft Project | Helps in project planning, scheduling, and tracking dependencies
GitHub Projects | Integrated with development workflows
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Release Summary 1
Iteration 1: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception PD | Iteration #1 PD | Iteration #2 PD | Iteration #3 PD | Transition PD
|  | Due: | Due: | Due: | Due: | Due:
1 | User Authentication | 4 | 2 | 0 | 0 | 0
2 | Volunteer Management | 4 | 2 | 0 | 0 | 0
3 | Donor Management | 4 | 2 | 0 | 0 | 0
4 | Event Management | 4 | 2 | 0 | 0 | 0
5 | Testing & Bug Fixes | 0 | 0 | 4 | 6 | 2
6 | Deployment & Documentation | 0 | 0 | 0 | 4 | 4
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 64 | 32 | 16 | 40 | 24
Total Project Hours |  | 176

## Agile Backlog 2
Iteration 2 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 1
101 | Advanced Donor Features | 5 | Backend & Frontend Developers
102 | Volunteer Certification | 4 | Developers
103 | Event-Volunteer Integration | 3 | UI/UX Designer
104 | Grant Application Module | 3 | API Developers
105 | Backend Integration | 3 | QA Team
Iteration 2
Iteration 3
Medium Priority
| Reporting Dashboard |  | Full Stack developer
Low Priority

## Iteration 2 Plan
Iteration Plan 2
Project | Designing a mobileApp for Nonprofit Management System
Team Names: | Global Scholars Team
Team Number: | G231
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
1 | Donor features | AP | yes
2 | Certifications | KP | yes
3 | UI/UX Enhancement | AP | yes
4 | Event integration | UM | yes
5 | Integration Testing | KP | yes
6 | bug fixes | AP | yes
7 | Grant module | UM | yes
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Frontend | API integration Bugs | KP
Backend | Scheduling Conflicts | UM
Database | Mobile Responsiveness | AP
Authentication | Data Security | KP
API Architecture | Team Sync | UM
UI Design Tool | Architrcture Deciions | AP
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
Jira or Trello | Used to create and assign tasks to team members
Allows for Sprint planning, task tracking and backlog refinement
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Release Summary 2
Iteration 2: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and tasks must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
1 | develop application workflow | 4 | 2 | 0 | 0 | 0
2 | integrate scheduling system | 4 | 2 | 0 | 0 | 0
3 | enhance UI/UX | 4 | 2 | 0 | 0 | 0
4 | backend integration | 4 | 2 | 0 | 0 | 0
5 | integration testing | 0 | 0 | 4 | 6 | 2
|  | 0 | 0 | 0 | 4 | 4
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 64 | 32 | 16 | 40 | 24
Total Project Hours |  | 176

## Iteration 3 Plan
Iteration Plan 3
Project | Designing a mobileApp for Nonprofit Management System
Team Names: | Global Scholars Team
Team Number: | G231
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
1 | System testing | AP/UM | yes
2 | User manuals | KP | yes
3 | Mobile adaption | KP | yes
4 | Deployment | UM | yes
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Mobile Framework | Perform issues | KP
Backend Scalability | Future user load | UM
Security | Data breaches, token misuse | AP
Database Desing | Data consistency and integrity | KP
APIs | Latency or data mistmatch | UM
Content Management | static text hardcoded | AP
Accessiblity | WCAG Compliance | KP
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
Github Repository | collaborate in branches
Daily Stand-ups | discuss blockers and align goals
Sprint Planning | ensuring continuous improvement
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Backlog 3
Iteration 3 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 1
301 | Comprehensive Testing | 5 | AP/UM
302 | Final Documentation | 4 | KP
303 | Mobile Responsiveness | 4 | KP
304 | Deployment Prep 4 | 3 | UM
Iteration 2
Iteration 3
Medium Priority
UI/UX Enhancement
Internal Assessment and Feedback Review
Low Priority

## Agile Release Summary 3
Iteration 3: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
| Regression Testing | 4 | 2 | 0 | 0 | 0
| Usability and Accessiblity Testing | 4 | 2 | 0 | 0 | 0
| Finalize Content and Error Message | 4 | 2 | 0 | 0 | 0
| Documentation | 4 | 2 | 0 | 0 | 0
| Beta Deployment | 0 | 0 | 4 | 6 | 2
| UI/UX Enhancements | 0 | 0 | 0 | 4 | 4
| Internal Assessment and Feedback Review | 0 | 0 | 4 | 0 | 4
| Sprint Review and Retrospective | 0 | 2 | 4 | 0 | 4
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 64 | 40 | 48 | 40 | 56
Total Project Hours |  | 248